## Tabelle1
Risk Name | Risk Description | Risk Probability of Occurrence | Risk Impact (1 = NEGLIGIBLE, 10 = LARGE) | Risk Factor | Risk Mitigation | Person in Charge of Tracking
Project definition | Scope of the project is too high to be fullfilled | MEDIUM | 10 | 20 | Keep track of progress | Huber, Marius
Unexpected scope change | Customer wants a large change | MEDIUM | 8 | 16 | Extensibility of code | Groß, Kolja
Backend dies | Server needs to be recovered via backup | LOW | 9 | 9 | Always do a backup | Schmuck, Niclas
Illness | A person gets ill and cant do the work | LOW | 5 | 5 | Physical distancing | Everyone
Stolen Device | Device of group member gets stolen | LOW | 3 | 3 | Use Laptoplock | Everyone
0
0
0
0
0
0
0
0
0
0